## CASS_Coverage
Total Script In All Domain
Domain | TOTAL SCRIPTS | US/CAN | PLANNED SCRIPTS | DIS CONTINUED | % COMPLETE
Smoke | 281 | USA - 127 | 249 | 32 | 100%
CAN - 122
GUI | 3198 | USA - 2049 | 2557 | 641 | 100%
CAN - 508
WUI | 237 | USA 172 | 203 | 34 | 100%
CAN - 31
STARS(USA) | 556 | 556 | 220 | 30 | 45%
STARS(CAN) | 458 | 458 | 10 | 0 | 2%
Total Automated Script
Domain | Total Test Cases/Scripts | Test Cases in Scope | Discontinued | Pass Rate
Smoke | 281 | 249 | 32 | 98%
GUI | 3198 | 2557 | 641 | 97%
WUI | 244 | 210 | 34 | 98%
STARS | 250 | 220 | 30 | 97%
Hybrid Framework Implementation Progress - STARS
TC Progress | Process Flow | Coverage % | Cummulative Coverage %
Total Process Flows | 43
Phase 1 | 11 | 25.58% | 25.58%
Phase 2 | 5 | 11.63% | 37.21%
Phase 3 | 8 | 18.6% | 55.81%
Phase 4 | 3 | 6.977% | 62.79%
Phase 5 | 4 | 9.302% | 72.09%
Phase 6 | 6 | 13.95% | 86.05%
Remaining | 6 | 13.95% | 100%
AI Use In Project
Project Name | No Flow | Completed | %Complete | AI Name
HCFI Letter Valiadion | 700 | 10 | 1.43% | Gemini 2.5 Flash
Automation Leverage
Task Type | Total Effort (Hours) | Automated Effort (Hours) | Manual Effort (Hours) | Automation Leverage %
New Enhancement &Maintenance & Debugging Script | 18 | 14 | 6 | 80%
Regression Suite Update | 15 | 12.75 | 2.25 | 85%

## CASS_Summary_Report
Automation Project – Summary Report Automation Tool Overview - In the Honda Finance project CASS (Customer Accounts Servicing System) is a core application used by Honda Finance Corporation (HFC) to manage customer loan. It supports applications for: • AHFC (American Honda Finance Corporation) – USA • HCFI (Honda Canada Finance Inc.) – Canada The application architecture consists of: • Frontend GUI developed on .NET • Backend database hosted on Mainframe • Payment interface integrated with Salesforce UFT (Unified Functional Testing) is used as the primary automation tool to automate end-to-end business scenarios across CASS and Mainframe systems. For test management and version control: ALM (Application Lifecycle Management) is used to manage test cases, test execution, defects, and reporting. • ALM is also used for storing and maintaining automation scripts and version history.
Automation Coverage The automation framework covers multiple domains including Smoke, GUI, WUI, and STARS with strong script-level and business-flow-level coverage. • Smoke Domain: 281 total scripts, 249 covered, 32 discontinued, with ~98% pass rate. • GUI Domain: 3,198 total scripts, 2,557 covered, 641 discontinued, with ~97% pass rate. • STARS (USA): 556 total scripts, 220 covered, 30 discontinued, with ~45% coverage. • STARS (Canada): 458 total scripts, 10 covered, 0 discontinued, with ~2% coverage. STARS consists of 43 end-to-end business process flows implemented using a hybrid automation framework. • Business Flow Coverage: More than 86% of business flows are automated (37 out of 43), which is higher then the client's expected target of 80% by March 2026. • Script-Based Coverage: • STARS (USA): ~45% • STARS (Canada): ~2%
Automation Activities • Release Execution: Monthaly releases automation execution is performed for full or partial across Smoke, GUI, WUI, and STARS domains. • Script Maintenance: Regular updates and stabilization of automation scripts to handle application changes. • HCFI Letter Valiadion: AI verifies 700+ dynamic letter templates by semantically matching CSV values against generated PDFs, ensuring each document visually “looks right” across layouts without manual effort. • Intelligent Automation: RSS automation is implemented to reduce manual effort and execution time. • Parallel Initiatives: • Ongoing Automation Projects: AHFC Automation, FCRA Automation, Salesforce Automation, RTC Automation • POC: Mobile Automation using Digital Lab •Innovations & Utilities: Developed multiple internal automation utilities to improve execution efficiency, test data availability, and environment stability.
Acknowledgement Mail for Innovations -
..\My Documents\Fw_ Acknowledgement Request for An Innovations.eml

## N-Origination_Coverage
Total Scripts in All Domain
Domain | Total Test Cases/Scripts | Pass Rate
Smoke | 136 | 99%
Regression | 2918 | 98%
Total Automated Script
Domain | Total Test Cases/Scenarios | Total test scripts automated
Ideal | 43 | 36
Origenate | 161 | 139
Innovations Accomplished
Innovation Name | %Complete | Tech Stack Used
PDF- UI Validation | 95% | Java-Selenium,spire.pdf
Letter Extraction | 100% | Python
NBB Extractor | 100% | Python
Test Design Studio | 100% | Python
Automation Leverage
Task Type | Coverage | Leverage
New Enhancement &Maintenance & Debugging Script | 85% | >80%

## Summary_Report_N-Origination
Automation Project – Summary Report Automation Tool Overview - In the Honda Finance project, N_Origination is a core application used by American Honda Finance Corporation (AHFC) to book customer loan. It supports applications for: • AHFC (American Honda Finance Corporation) – USA The application architecture consists of: • Ideal Frontend developed on Java • Origenate Frontend developed on Java Script Selenium(Java) is used as the primary automation tool to automate end-to-end business scenarios across applications. For test management and version control: ALM (Application Lifecycle Management) is used to manage test cases, test execution, defects, and reporting. AZURE DevOps is used for storing and maintaining automation scripts and version history .It is also used for regression and smoke pipelines .
Automation Coverage The automation framework includes Smoke and regression testcases with strong script-level and business-flow-level coverage. • Smoke : 136 total scripts with ~99% pass rate. • Regression : 2918 total scripts with ~98% pass rate. • E-2-E business process flows implemented using a hybrid automation framework. • Business Flow Coverage: More than 85% of business flows are automated (175 out of 204).
Automation Activities • Release Execution: Bi-weekly releases automation regression is performed for Ideal application and Monthly regression for Origenate Application. • Script Maintenance: Regular updates and stabilization of automation scripts to handle application changes. • Smoke Validation: Performing daily smoke test to verify the environment stability. • Parallel Initiatives: • Ongoing Automation Projects: DSP Automation • POC: Test Case generation, Test Script generation using Github Copilot •Innovations & Utilities: Letter extraction, NBB Extractor,PDF-UI Validator,Law Form utility(On-going),Combination Suggestor(On - going)